## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.2 | 1.2.1 (a), 1.2.1 (b), 1.2.1 (c), 1.2.2, 1.2.3 | Information available through internet | 30 June 2021 | 30 June 2026 | Yes | Yes | WB |  Undertake a study to take stock of the range of publications produced by various institutions, and assess the gaps.  Prepare and implement guidelines and standard operating procedures for the publication of trade-related information.  Assistance to prepare a description of the practical steps involved in import, export, transit and appeal procedures for each relevant border agency, and to identify all the documents required. | Information and communication technologies (ICT), Legislative and regulatory framework, Diagnostic and Needs Assessment
5.3 | 5.3.1, 5.3.2, 5.3.3 | Test procedures | 30 June 2022 | 30 June 2024 | Yes | No |  |  Amend the relevant laws/regulations and ensure that traders have access to a second test.  Help to develop accreditation criteria and/or to identify laboratories equipped to carry out the relevant test procedures.  Develop standard operating procedures, particularly those pertaining to appropriate sampling techniques and the handling of results that contradict the results of the second test.  Human resources/training: capacity building for the border agencies, laboratories/technicians and traders involved. | Legislative and regulatory framework, Human resources and training
6.1 | 6.1.1, 6.1.2, 6.1.3, 6.1.4 | General disciplines on fees and charges | 30 June 2021 | 30 June 2026 | Yes | Yes | WB |  Develop competence in the use of methodologies for quantifying costs in order to justify fees and charges.  Develop a comprehensive training programme to periodically assess existing and new fees and charges.  Draw up and publish a single schedule of all fees and charges related to imports and exports. | Information and communication technologies (ICT)
6.2 | 6.2 (i), 6.2 (ii) | Specific disciplines on fees and charges | 30 June 2021 | 30 June 2026 | Yes | No |  |  Technical assistance for the mapping and costing of services rendered by the customs authorities, including the development of a fair and transparent fee structure. | Legislative and regulatory framework, Human resources and training
7.4 | 7.4.1, 7.4.2, 7.4.3, 7.4.4 | Risk management | 30 June 2022 | 30 June 2026 | Yes | No |  |  Review of the profiling mechanism and procedures of customs and other government agencies.  Training and capacity building for border agencies on risk management.  Establishment of an ICT infrastructure to support the national risk management framework.  Development of a multi-agency risk management framework. | Information and communication technologies (ICT), Legislative and regulatory framework, Institutional procedures, Human resources and training
7.7 | 7.7.1, 7.7.2 (a) (i), 7.7.2 (a) (ii), 7.7.2 (a) (iii), 7.7.2 (a) (iv), 7.7.2 (b) (i), 7.7.2 (b) (ii), 7.7.3 (a), 7.7.3 (b), 7.7.3 (c), 7.7.3 (d), 7.7.3 (e), 7.7.3 (f), 7.7.3 (g), 7.7.4, 7.7.5, 7.7.6 | Authorized operators | 30 June 2021 | 30 June 2023 | Yes | Yes |  |  Awareness-raising among private sector stakeholders.  Change management.  Development of a national mechanism for coordination and cooperation between customs and other border agencies. | Legislative and regulatory framework, Institutional procedures, Awareness-raising
8 | 8.1, 8.2 (a), 8.2 (b), 8.2 (c), 8.2 (d), 8.2 (e) | Border Agency Cooperation | 30 June 2023 | 30 June 2026 | Yes | No |  |  Review existing cooperation mechanisms both within Angola and across borders.  Human and institutional capacity building for coordinated border management.  Funding of border agencies.  ICT | Information and communication technologies (ICT), Legislative and regulatory framework, Human resources and training
10.2 | 10.2.1, 10.2.2, 10.2.3 | Acceptance of copies | 30 June 2021 | 30 June 2023 | Yes | No |  |  Review and amend legislation if necessary.  Draw up regulations and instructions.  Training of officials.  Awareness-raising programme for notification of fees. | Legislative and regulatory framework, Institutional procedures, Human resources and training, Awareness-raising
10.4 | 10.4.1, 10.4.2, 10.4.3, 10.4.4 | Single window | 30 June 2023 | 30 June 2027 | Yes | No |  |  ICT infrastructure.  Institutional capacity building.  Training of personnel and awareness-raising. | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
10.6 | 10.6.1, 10.6.2, 10.6.3 | Use of customs brokers | 30 June 2022 | 30 June 2026 | Yes | No |  |  Review licensing requirements to ensure that they are objective and transparent.  Training on publication requirements. | Legislative and regulatory framework, Human resources and training