## Worksheet
Measure | Items | Measure name | Indicative Implementation Date | Definitive Implementation Date | TA needs notified | Progress reported | Donor / Agency | TA Description | Tags
1.2 | 1.2.1 (a), 1.2.1 (b), 1.2.1 (c), 1.2.2, 1.2.3 | Information available through internet | 22 February 2021 | 31 December 2025 | Yes | No |  | Legal/Policy  Undertake study to include stocktake of all trade information available online; identify gaps and assess Samoa's readiness to have a trade information portal/ website; cost and benefit analysis. Develop policy and legislate as necessary the mandate and process of publishing information; and having this information available online Procedures  Review of outdated Standard Operating Procedures Human Resources/Training  Training of IT Staff to design, develop and maintain websites  Training of Customs officials on the implementation of Standard Operating Procedures  Relevant training of officials and private sector Information and Communication Technology  Develop and maintain a Trade Information Portal system (TIP) Infrastructure  Appropriate equipment and software programs for border agencies Consultations/Public Awareness  Stakeholder consultations on the potential TIP | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Diagnostic and Needs Assessment, Human resources and training, Awareness-raising
4 | 4.1 (a), 4.1 (b), 4.2, 4.3, 4.4 (a), 4.4 (b), 4.4 end paragraph, 4.5, 4.6 | Procedures for appeal or review | 22 February 2020 | 31 December 2027 | Yes | No |  | Operation  Financial (and technical support where relevant) assistance required for the initial set-up and operation of the Customs Appeal Authority for the first five years | Information and communication technologies (ICT), Legislative and regulatory framework
6.3 | 6.3.1, 6.3.2, 6.3.3, 6.3.4 (a), 6.3.4 (b), 6.3.5, 6.3.6, 6.3.7 | Penalty Disciplines | 31 December 2019 | 31 December 2025 | Yes | No |  | Human resources/Training  Capacity building and training for Customs officials on the implementation and application of this provision | Human resources and training
7.1 | 7.1.1, 7.1.2 | Pre-arrival processing | 30 June 2019 | 31 December 2025 | Yes | No |  | Human Resources/Training  Capacity building and training for Customs, Quarantine Biosecurity and Border agencies officials on the implementation and application of this provision Information and Communication Technology  Enhance the technological capacity of Customs officials in implementing this provision Infrastructure  Upgrade existing Customs and Border agencies systems and infrastructure to facilitate Pre-arrival processing  Upgrade and improvements to existing Quarantine Biosecurity infrastructure to facilitate pre-arrival processing | Information and communication technologies (ICT), Infrastructure and equipment, Human resources and training
7.2 | 7.2 | Electronic payment | 22 February 2020 | 31 December 2027 | Yes | No |  | Legal/Policy  Review existing systems and policies. And determine feasibility and resources required to set-up and operate an electronic payment system Human Resources/Training  Capacity building and training for Customs, Quarantine Biosecurity and Border agencies officials on electronic payment Information and Communication Technology  Enhance technological capacity of border agencies and government agencies necessary to implement an electronic payment system Infrastructure  Development, set-up and installation of appropriate technology and equipment to put in place an electronic payment system | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
7.4 | 7.4.1, 7.4.2, 7.4.3, 7.4.4 | Risk management | 22 February 2023 | 31 December 2027 | Yes | No |  | Legal  Review/develop legal basis to enhance coordination and collaboration between border agencies on risk identification and application of risk management Policy  Develop a risk management policy with target percentages of low/high risk cargo  Develop a training plan for Customs, Quarantine Biosecurity and Border agencies officials on risk management targeting the application of risk management Procedures  Review and develop necessary procedures Human Resources/Training  Capacity building and training for Customs and Quarantine Biosecurity officials on risk management using transaction data from ASYCUDA system  Training and Development for border agencies staff on risk identification and profiling Information and Communication Technology  Enhance technological capacity of Border agencies necessary to implement a proper risk management process/system Infrastructure  Provision of Non -Intrusive Inspection equipment  Provision of appropriate technology and equipment to support the implementation of a proper risk management system | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Institutional procedures, Human resources and training
7.5 | 7.5.1, 7.5.2, 7.5.3, 7.5.4 | Post-clearance audit | 22 February 2023 | 31 December 2027 | Yes | No |  | Legal  Develop/review relevant legislations and policies for Post Clearance Audit (PCA) Policy  Develop a compliance assessment policy and procedure incorporating the connectivity with risk management  Develop a training plan/module to train Customs officials and agents on the concept of 'informed compliance' and train the target groups  Develop a methodology/approach to conduct a national compliance assessment on an annual basis Procedures Develop and update processes and procedures that incorporate these aspects of PCA:  Draft a compliance assessment policy and procedure incorporating the connectivity with risk management  Draft a training module to train Customs and the Agents on the concept of 'informed compliance' and train the target groups  Draft a methodology/approach to conduct a compliance assessment on an annual basis for the whole of Samoa  Conduct annual compliance assessments  Train Customs staff to conduct PCA as a compliance assessment tool Human Resources/Training  Capacity building and training for Customs officials to conduct Post Clearance Audit as a compliance assessment tool  Develop data analysis skills and knowledge for Customs and border agencies officials  Capacity building and training for Customs PCA officials on auditing techniques and methodology Information and Communication Technology  Enhance technological capacity of Border agencies necessary to implement PCA Infrastructure  Provision of appropriate technology and equipment to help implement PCA | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
7.7 | 7.7.1, 7.7.2 (a) (i), 7.7.2 (a) (ii), 7.7.2 (a) (iii), 7.7.2 (a) (iv), 7.7.2 (b) (i), 7.7.2 (b) (ii), 7.7.3 (a), 7.7.3 (b), 7.7.3 (c), 7.7.3 (d), 7.7.3 (e), 7.7.3 (f), 7.7.3 (g), 7.7.4, 7.7.5, 7.7.6 | Authorized operators | 22 February 2023 | 31 December 2026 | Yes | No |  | Legal  Develop relevant legislation and policies to allow the setup of an Authorised Operators (AO) program Policy  Develop an Authorised Operators policy Procedures  Develop proper procedures and criteria for the assessment of authorised operators that meet specified criteria in the AO program Human Resources/Training  Capacity building and training for Customs and Quarantine officials on the implementation of the AO program | Legislative and regulatory framework, Human resources and training
7.8 | 7.8.1 (a), 7.8.1 (b), 7.8.1 (c), 7.8.1 (d), 7.8.1 (e), 7.8.1 (f), 7.8.1 (g), 7.8.1 (h), 7.8.2 (a), 7.8.2 (b), 7.8.2 (c), 7.8.2 (d), 7.8.3 | Expedited shipments | 22 February 2020 | 31 December 2027 | Yes | No |  | Legal/Policy  Develop relevant legislation and policies Procedures  Review of outdated Standard Operating Procedures Human Resources/Training  Training of Customs and Border agencies officials on clearance of commercial cargos at the airports  Training of Customs officials on the implementation of Standard Operating Procedures Infrastructure  Appropriate equipment required such as x-rays, scanners and computers for border agencies | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Diagnostic and Needs Assessment, Human resources and training
8 | 8.1, 8.2 (a), 8.2 (b), 8.2 (c), 8.2 (d), 8.2 (e) | Border Agency Cooperation | 22 February 2019 | 31 December 2025 | Yes | No |  | Legal/Policy • Review and identify gaps in the existing system of coordination and policies • Review/develop legal basis to enhance coordination and collaboration between border agencies Procedures • Develop Procedures and Memorandum of Understanding (MOU) to help enhance the cooperation of border agencies Human Resources/Training • Capacity building and training for Border agencies officials on a new coordinated approach | Legislative and regulatory framework, Diagnostic and Needs Assessment, Institutional procedures, Human resources and training
10.1 | 10.1.1 (a), 10.1.1 (b), 10.1.1 (c), 10.1.1 (d) | Formalities | 22 February 2020 | 31 December 2027 | Yes | No |  | Policy  Support to customs to expedite publication and activation of the new draft procedures under the modernization program Information and Communication Technology  Enhance the technological capacity of Customs and border agencies officials to ensure full utilisation of the ASYCUDA World system Infrastructure  Upgrade existing Customs system and infrastructure to implement this provision | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Human resources and training
10.4 | 10.4.1, 10.4.2, 10.4.3, 10.4.4 | Single window | 22 February 2022 | 31 December 2040 | Yes | No |  | Legal  Review/develop relevant laws to facilitate the development of a comprehensive national single window  Compliance review  Develop Memorandum of Understanding (MOUs) with other agencies to enhance cooperation Policy  Conduct a feasibility study to explore the viability of a national single window system  Develop a strategy for the implementation of single window Procedures  Develop appropriate procedures and processes to facilitate the implementation of single window Human Resources/Training  Capacity building and training for Customs officials and border agencies on the implementation of single window system  Capacity building for other government agencies and private sector on the implementation of single window system Information and Communication Technology  Review of national ICT policies to facilitate the implementation of single window  Enhance and upgrade technological capabilities of border agencies and government agencies necessary to implement the single window Infrastructure  Provision of appropriate technology and equipment to help implement single window | Information and communication technologies (ICT), Legislative and regulatory framework, Infrastructure and equipment, Diagnostic and Needs Assessment, Human resources and training